## Slide 1
Risk Assessment Workbench
Genius Hacks Q3 2026 — Project Schedule
September 14 – September 30, 2026 · 4 Developers · 17 Days
DEV 1
DEV 2
DEV 3
DEV 4

## Slide 2
Program Overview
Six delivery stages across the full schedule (Sept 14 – Sept 30)
Sep 14
Mon
Sep 15
Tue
Sep 16
Wed
Sep 17
Thu
Sep 18
Fri
Sep 19
Sat
Sep 20
Sun
Sep 21
Mon
Sep 22
Tue
Sep 23
Wed
Sep 24
Thu
Sep 25
Fri
Sep 26
Sat
Sep 27
Sun
Sep 28
Mon
Sep 29
Tue
Requirement Expansion (all)
Design & Architecture (all, shared)
Development (per-developer workstreams)
Testing & Evaluation (overlapping)
Deployment
Operations & Observability
Packaging, Rehearsal & Submission
Kickoff
Submit

## Slide 3
Week 1 Detail — Shared Design & Architecture
All four developers work together before splitting into workstreams
Sep 14
Mon
Sep 15
Tue
Sep 16
Wed
Sep 17
Thu
Sep 18
Fri
Kickoff & requirement-expansion workshop (Sep 14–15)
Agent & system architecture design (Sep 15–17)
Synthetic data model & governance framework design (Sep 16–18)
Evaluation framework design (Sep 17–18)
Split into workstreams

## Slide 4
Detailed Schedule — Developers 1 & 2
Sept 18 – Sept 29
Sep 18
Fri
Sep 19
Sat
Sep 20
Sun
Sep 21
Mon
Sep 22
Tue
Sep 23
Wed
Sep 24
Thu
Sep 25
Fri
Sep 26
Sat
Sep 27
Sun
Sep 28
Mon
Sep 29
Tue
DEV 1 — AGENT ORCHESTRATION & AI HARNESS
Agent framework skeleton setup (LangGraph) (18–19)
Build intake / requirements agent (19–21)
Build risk-scoring agent + RAG hookup (21–24)
Build governance / human-review-gate agent (24–26)
Orchestration integration & prompt tuning (26–28)
Support integration testing & polish (28–29)
DEV 2 — DOMAIN, DATA & RETRIEVAL
Research supervisory risk-scoring frameworks (18–19)
Generate synthetic data sets (19–21)
Build RAG / retrieval layer (embeddings, vector store) (21–24)
Validate risk-scoring methodology vs. framework (24–26)
Finalize requirement-expansion document (26–27)
Support eval test-data prep & polish (27–29)
Submit

## Slide 5
Detailed Schedule — Developers 3 & 4, Final Integration
Sept 18 – Sept 30
Sep 18
Fri
Sep 19
Sat
Sep 20
Sun
Sep 21
Mon
Sep 22
Tue
Sep 23
Wed
Sep 24
Thu
Sep 25
Fri
Sep 26
Sat
Sep 27
Sun
Sep 28
Mon
Sep 29
Tue
DEV 3 — APPLICATION, INTEGRATION & DEPLOYMENT
Workbench UI wireframes & project setup (18–19)
API layer & agent integration hooks (19–22)
Build workbench UI: dashboard & review queue (22–25)
Containerize app (Docker) & CI pipeline (25–27)
Deployment spec & production readiness checklist (27–28)
Support integration testing & polish (28–29)
DEV 4 — EVALUATION, GOVERNANCE & OBSERVABILITY
Set up eval harness: Ragas/DeepEval + Langfuse (18–20)
Build test suite: unit & integration (20–23)
Write governance framework documentation (23–25)
Build observability & monitoring dashboards (25–27)
Finalize architecture diagrams (27–28)
Build presentation deck & coordinate rehearsal (28–29)
ALL DEVELOPERS — FINAL INTEGRATION
Full integration testing & demo rehearsal (28–29)
Submission packaging & final review (29–30)
Submit